## 7-3-2013
Feature name | Comment | Use Case | Subsystem | Effort | For 1/5 | Type | Initial priority | Can postpone? | Ready for dev
Thumbnails |  | Sequence + Seperator Use Case | CGS | 10 | 10 | Product | 1 |  | In process
Refactor |  | - | CGS | 9 | 9 | Product | 1 |  | In process
Copy/ Cut/ Paste |  | TOC: Move/Cut/Paste Item | CGS | 5 | 5 | Product | 1 |  | In process
Creative selection in sequence |  | Sequence + Seperator Use Case | CGS | 2 | 2 | Product | 2 |  | In process
Checkable applet |  | Content Editing: Edit Checkable Applet Task | CGS | 5 | 5 | Product | 1 |  | Yes
Schema changes | LO/ Sequence level changes | TOC | CGS | 15 | 15 | Product | 1
Differentiation |  | Attributes: Differentiation | CGS | 10 | 10 | Product | 1
Assessment |  | ? | CGS | 20 | 20 | Product | 1
Assessment applet task | Support as open question | ? | DL | 4 | 4 | Product | 1
DTP assessment integration |  | ? | DL | 12 | 12 | Product | 1
Standards tagging |  | Content Editing: Manage Standards and Skills | CGS | 20 | 20 | Product | 1
DL component grouping | Declare two components to be side by side |  | CGS + DL | 15 | 15 | Product | 1 | Consult (Editis)
third party sequence | URL/ HTML/ PDF | ? | CGS | 10 | 10 | Product | 1
third party sequence | URL/ HTML/ PDF (Player support) | ? | DL | 5 | 5 | Product | 1
Pluggable editors infrastructure | Must before implementing new templates - meeting follow up |  | CGS + DL | 15 | 15 | Product | 1 | Consult (Editis) | Yes
Matching |  | ? | CGS | 9 | 9 | Feature | 1 |  | In process
Cloze | Must be implemented as external | Content Editing: Edit Editors: Cloze | CGS | 15 | 15 | Feature | 1
Bank editor - Cloze | Must be implemented as external | ? | CGS | 10 | 10 | Feature | 1
Table |  | Content Editing: Edit Table | CGS | 15 | 15 | Feature | 1

## 1-3-2013
Subsystem | Category | Feature Name | Use Case | Estimate | Beta - 1- May - 2013 | Beta + 1 month (CQA - Play) | 7.0X | Comments
CGS | Editors | Table | Content Editing: Edit Table | 15 | 15
CGS | Editors | Shared | Content Editing: Edit Shared | 0 | 0
CGS | Editors | Cloze | Content Editing: Edit Editors: Cloze | 15 | 15
CGS | Editors | Matching | Content Editing: Edit Matching | 15 | 15
CGS | Editors | Sorting | Content Editing: Edit Sorting | 15 | 10
CGS | Editors | Checkable applet task | Content Editing: Edit Checkable Applet Task | 10 | 10 |  |  | Lizou - See if we can do without applet checking (Like OPQ) + Guidelines - Remove 10 days
CGS | Editors | Sequencing | Content Editing: Edit Sequence | 15 | 10 |  |  | Yuval - See whether estimates are less for matching/ sorting/ seq. - Reduce 15 days
CGS | Editors | Third party sequence | Content Editing: Edit Sequence | 10 | 10 |  |  | Lizou - can we rescope: PDF , URL, HTML
CGS | Editors | Bank editor | Content Editing: Edit Bank Editor | 20 | 20
CGS | Editors | Help editor | Content Editing: Edit Help Editor | 10 | 10
CGS | Editors | Teacher's guide for TOC | Content Editing: Edit Teacher Guide for TOC | 12 | 12 |  |  | Sync with DTP 7.0.0
CGS | Editors | Task list - Shared arrangement | Content Editing: Edit Task List | 2 | 2
CGS | Editors | Glossary | Content Editing: Glossary | 20 | 10
CGS | Editors | Dialog component | Content Editing: Dialog Component | 15 | 15
CGS | Editors | Show answer for teacher - OPQ, Question only | Content Editing: Edit Show answer for teacher: OPQ | 10 | 10 |  |  | Lizou - verify that we can use "Teacher Instauration" as a solution Sync with DTP7.0.0
CGS | Editors | Assessment |  | 20 | 20 |  |  | Assessment support includes: scoring (MC, Cloze/Completion & Open) , properties, several tasks in seq
CGS | Attributes | Differentiation | Attributes: Differentiation | 6 | 6
CGS | Attributes | Standards and skills editing | Content Editing: Manage Standards and Skills | 20 | 20 |  |  | Support for HTML text Who is going to prepare and provide will provide the
CGS | Attributes | Creative selection in sequence | Sequence + Seperator Use Case | 10 | 10
CGS | General | Hebrew and RTL content creation | Non Functional: General: Hebrew and RTL content creation | 35 | 0 |  | 35
CGS | General | Math signs localization for Hebrew | Non Functional: General: Math signs localization for Hebrew | 5 | 0 |  | 5
CGS | General | Asset management integration | Assets Use Case | 20 | 20 |  |  | Lizou's feedback must for producation
CGS | General | Catalog/ Publishing integration | Publish Course | 15 | 15
CGS | General | PDF import (PDF to AI) | PDF2Course Use Case | 80 | 100
CGS | General | Thumbnail generation | Sequence + Seperator Use Case | Yuval EE | 0 |  | Yuval EE
CGS | General | Copy & paste + Drag & Drop TOC | TOC: Move/Cut/Paste Item | 12 | 12
CGS | General | Copy & paste + Drag & Drop Lesson | TOC: Move/Cut/Paste Item | 8 | 8
CGS | General | Copy & paste + Drag & Drop Sequence | TOC: Move/Cut/Paste Item | 6 | 6
CGS | General | Undo/ Redo |  | 7 | 0
CGS | General | Lesson template support | Content Editing: Lesson Tempalate Support | 14 | 0 |  |  | Lizou -check if use a workaround like copy paste from master lesson
CGS | Alpha feedback | UI Enhancements | Non Functional: Alpha feedback: UI Enhancements | 8 | 0 |  | 8 | Liad - alpha feedback
CGS | Alpha feedback | GUI Enhancements | Non Functional: Alpha feedback: GUI Enhancements | 7 | 0 |  | 7 | Liad - alpha feedback
CGS | Alpha feedback | Metadata Enhancements | Non Functional: Alpha feedback: Metadata Enhancements | 10 | 0 |  | 10 | Liad - alpha feedback
CGS | General | Lesson Preview (DTP Simulation) | Preview Content | 10 | 10 |  |  | Lizou's input - production need this for 7-Apr -2013
Player | General | Teacher - Show answer |  | 10 | 10 |  | Yuval EE | Yuval - verify that feature support later than 7.0.0 has no effect on production work - no rework
Player | General | Skip tasks in sequence |  | Yuval EE | 0 |  | Yuval EE | Yuval - verify that feature support later than 7.0.0 has no effect on production work - no rework
Player | General | Help |  | 8 | 8
Player | General | Third party sequence |  | 20 | 5 |  |  | ** PDF as attachment for print. If presentation required then PDF->'T2K page' duirng content creation
Player | General | Task list - Shared arrangement |  | 5 | 5
Player | General | Caption and credits for video |  | 5 | 5
Player | Math | Pi (As a number replacement) | Non Functional: Math: Pi | 5 | 5
Player | Math | Algebraic expressions | Non Functional: Math: Algebraic expressions | 10 | 10
Player | Assessment | MARC integration |  | 12 | 0 |  | 12 | sync with DTP7.0.0 (MARC) | sync with DTP MARC (ask Shlomit)
Player | Assessment | Presenting applets |  | 2 | 2
Player | Assessment | Sequence in assessment |  | 12 | 12
Player | Assessment | Cloze support |  | 14 | 14 |  |  | Lizou's input - production need this no later than 14-Apr 2013 | no later then 14-Apr 2013